## Slide 1: Inclusive Data Principles 1 and 2 key commitments
IDP and key objectives (status R/A/G) |  | 2022 Jan | Apr | Jul | Oct | 2023 Jan | Apr | Jul | Oct | 2024 Jan | Apr | Jul | Oct | 2025 Jan | Apr
IDP1 (G) | Enhance trust and trustworthiness (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IDP2 (G) | Governance and monitoring (Green/Amber) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | International engagement (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop ‘Social Contract’
Improve engagement with currently under-represented population groups
Improve Workforce Diversity in ONS/Departments/Government
Establish National Statistician’s Advisory Committee
C
Establish cross-Government Statistical Service sub-committee
Inclusive Data Taskforce
Implementation Roadmap
Progress summary: Positive progress continues to be made across the Inclusive Data Principles. Seven are ‘Green’ (on track); IDP 4 is Amber/Green (due to delays to the intersectional analysis work, see slide 5); since last quarter IDP 1 and IDP 3 have revised from Amber/Green to Green as work is progressing against new timescales.
Establish United Nations City Group on inclusivity
Explore feasibility
Scoping and engagement
C
Establish ONS Assembly
Establish Engagement Hub
Community outreach programme
C
C
Digital Public Engagement with Data campaign
Develop and deliver inclusive leadership training to field force managers
A
R
Will not be delivered without action
Key:
Not started
G
Good progress, on track to deliver
A
All or some of commitment has been delayed
C
Completed/delivered
To minimise complexity, commitments are being led by ONS unless otherwise indicated
Decision point, when future work will be agreed
Planned – subject to scoping/funding
Confirmed programme of work
Meeting of Committee/ Assembly
Future activities to engage public in data
G
G
Government Analysis Function - inclusion toolkits; training and development programmes for under-represented groups
Establish whole UK statistical system approach
G
Scoping requirements
Initial outputs
G
A
G
G

## Slide 2: Inclusive Data Principle 3 key commitments
IDP and key objectives (status) | Principles and key objectives (status) | 2022 Jan | Apr | Jul | Oct | 2023 Jan | Apr | Jul | Oct | 2024 Jan | Apr | Jul | Oct | 2025 Jan | Apr
IDP3 (G) | Improve coverage of non-private household populations (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Identify and address under-represented groups (Amber/Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Improve inclusivity of admin data (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Improve evidence base on people living in communal establishments
Review existing data sources for communal establishments and other special population groups
Explore feasibility of collecting survey data from non-private household populations
R
Explore feasibility of individual-level homelessness data in Wales and expansion of data collection across Wales
G
Set-up mechanism to regularly review under-representation in UK statistics
Use 2021 Census to assess representativeness of key data sources
G
Cabinet Office - Publish analysis and recommendation to address non-response bias
HMRC: Evaluate approach to collection of protected characteristics data
G
Home Office and ONS jointly working to include refugees in migration statistics
Scope and procure research to identify hidden homeless groups
G
Agree next steps/priority area for review
Improve coverage of homelessness in UK data
Methodological review of estimating homelessness (Scottish Gov)
A
Census 2021 non-household analysis
G
G
Click here to see Key
Evidence review of hidden homelessness in the UK
C
Introduce Adaptive Survey Design to Transformed Labour Force Survey to drive-up response from under-represented groups.
Paused awaiting outcome of ONS review of existing data sources and subject to resourcing
Consider roll out to other household surveys.
C
Refugee Integration Outcomes (RIO) study: initial data linkage
Broaden access and link additional data sets
C
G
G
Cabinet Office – Implement National survey of disabled people (subject to funding)
R
Research into hidden homelessness in Scotland
G

## Slide 3: Inclusive Data Principles 3 and 4 key commitments
IDP and key objectives (status) | Principles and key objectives (status) | 2022 Jan | Apr | Jul | Oct | 2023 Jan | Apr | Jul | Oct | 2024 Jan | Apr | Jul | Oct | 2025 Jan | Apr
IDP3 (G) | Cross-cutting data improvement programmes (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IDP4 (A/G) | Improve the granularity of data to enable meaningful disaggregation (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Promote an intersectional approach (Amber) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DfE - Introduce individual level Education, Health and Care plan data collection
G
DfE - Introduce targeted oversampling of under-represented/disadvantaged groups
G
CO/RDU - Review granularity of existing datasets
Equality Data Asset proof of concept: linking data to enable analysis (prototype)
C
Development of Intersectional Analysis methods
R
Agree next steps using
Integrated Data Service
Develop improvement plans
Develop social inclusion strategies and associated actions plans for Northern Ireland
G
Strengthen equality evidence to address inequality in Wales
Develop Equality Evidence Strategy
C
Scottish Government Equality Data Improvement Programme
C
Continue to strengthen equality evidence to address inequality in Northern Ireland
Decide next steps
Enable intersectional approach to analysis
Click here to see Key
Develop Equality Evidence Strategy 2023-25
C
Impact of Anti-Racist Wales Action Plan
Personal characteristics of Public Sector Boards
G
Develop recommendations (Inclusive Britain Action 7)
C
G
G
Decide next steps

## Slide 4: Inclusive Data Principles 5 and 6 key commitments
IDP and key objectives (status) | Principles and key objectives (status) | 2022 Jan | Apr | Jul | Oct | 2023 Jan | Apr | Jul | Oct | 2024 Jan | Apr | Jul | Oct | 2025 Jan | Apr
IDP5 (G) | Ensure measures accurately reflect current standards (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IDP6 (G) | Widen the range of methods (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Use data linkage to enable enhanced analysis (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
12 week
Public Consultation
Transformation of population and migration statistics
Development of Integrated Data Service
National Statistician’s Recommendation on future of population statistics/Census
Programme of qualitative work with seldom heard groups
Disabled adults access to services
Children with Special Educational Needs and Disabilities
Gypsy and Traveller Community
Domestic abuse survivors in temporary ‘safe’ accommodation
Young migrants and refugees
G
G
G
C
C
C
Decision on next topic/s
Explore and implement innovative methods including more qualitative research
Click here to see Key
Develop and implement Integrated Data Service (IDS)
Enhance IDS capabilities
G
Improving scope and outputs, meeting unmet user needs
Enhance availability of longitudinal data to better understand life outcomes (proof of concept)
More timely multivariate statistics (proof of concept)
Increased timeliness of population statistics
(proof of concept)
G
G
WG - Research on how information can be collected to reflect the social model of disability
A
Update Harmonisation standards and guidance for data in line with societal change
Updated ethnicity standard (online mode)
Redesign: Disability standard (online mode)
Research on: disability (A), ethnicity (A), mental health (A) and gender identity (C)
Updated sex and gender identity guidance
New socio-economic background standard (online mode)
Updated ethnicity standard (face-to-face and telephone modes)
Design new mental health standard
G
C
G
C
Updated Welsh Language, National Identity and Religion standards
C
Review and update sexual orientation standard
G
Frameworks for quality assessment and improvement
G
G
G
Updated gender identity standard (face-to-face and telephone modes)
Developing support to data collectors and processors to harmonise administrative data
G
Updated Disability standard (face-to-face and telephone modes)

## Slide 5: Inclusive Data Principles 7 and 8 key commitments
IDP and key objectives (status) | Principles and key objectives (status) | 2022 Jan | Apr | Jul | Oct | 2023 Jan | Apr | Jul | Oct | 2024 Jan | Apr | Jul | Oct | 2025 Jan | Apr
IDP7 (G) | Regular review of harmonised standards (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Harmonisation and comparability of data (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IDP8 (G) | Access to administrative data (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tools to improve accessibility of data (Green) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Explore feasibility of developing equality data and analysis tool
Flexible table builder developed and published – Census 2021 data
C
G
Plan next steps
Improve accessibility to data on equalities
Click here to see Key
Implement mechanism for regular review of definitions for data collection
Continue GSS Coherence Work Programme
Review and publish harmonisation priorities for the next two years
Publish 2022-23 Coherence Work Programme
C
Review and publish coherence priorities
Publish GSS Harmonisation 2022 Plan
Priorities include data on Adult Social Care, and Income and earnings
G
Work on priorities as appropriate
Implement GSS Harmonisation Review Plan (see IDP 5)
G
C
Inclusive Data Principle – Status (Where Red or Amber) |  | Reason for status and getting back to Green
IDP4 (A) | Improve the UK data infrastructure to enable robust and reliable disaggregation and intersectional analysis across the full range of relevant groups and populations, and at differing levels of geography. | Work to develop intersectional analysis methods has been paused due to prioritisation of work across the ONS, with work planned to recommence in 2023/4 subject to resourcing demands.
Please note: All publication dates/timelines are currently provisional and not for public view or wider circulation